## RTM
SkillUp LMS — Phase 1 Requirements Traceability Matrix
Generated 2026-06-08 · Maps each FR to the user story, screen, components, business rules, edge cases, AC count, priority, and phase.
FR ID | Story ID | Story Title | Epic | Screen Ref (Figma) | Components | Business Rules | Edge Cases | Priority | Phase | AC Count | Status
FR-001 | P1-01 | See enrolled courses on dashboard | E1 Dashboard | My Learning | Course Card | BR-30 | — | P0 | Phase 1 | 2 | Draft
FR-002 | P1-02 | Resume last viewed topic | E1 Dashboard | My Learning | Course Card | — | — | P0 | Phase 1 | 2 | Draft
FR-003 | P1-03 | See next-live indicator within 7 days | E1 Dashboard | My Learning | Course Card · Live Strip | BR-31 | — | P1 | Phase 1 | 3 | Draft
FR-004 | P1-04 | See course metadata at a glance | E1 Dashboard | My Learning | Course Card · Badges | — | — | P0 | Phase 1 | 1 | Draft
FR-005 | P1-05 | Navigate course via sidebar | E2 Player chrome | Video player screens | Sidebar v2 (Expanded) | BR-06, BR-34 | — | P0 | Phase 1 | 3 | Draft
FR-006 | P1-06 | Collapse sidebar | E2 Player chrome | Video player screens | Sidebar v2 (Collapsed) | — | — | P0 | Phase 1 | 2 | Draft
FR-007 | P1-07 | Mobile sidebar drawer | E2 Player chrome | Mobile variants | Sidebar v2 (Mobile) | — | EC-17 | P0 | Phase 1 | 2 | Draft
FR-008 | P1-08 | Course progress in topbar | E2 Player chrome | All player screens | Course Player Topbar | — | — | P0 | Phase 1 | 2 | Draft
FR-009 | P1-09 | Open AI panel | E2 Player chrome | All player screens | AI Panel (Ask/Chat/Related) | — | EC-37, EC-38, EC-39 | P1 | Phase 1 | 2 | Draft
FR-010 | P1-10 | Play/pause video | E3 Video | Video · Transcript | Video Player | — | — | P0 | Phase 1 | 2 | Draft
FR-011 | P1-11 | Seek video | E3 Video | Video · Transcript | Video Player | — | — | P0 | Phase 1 | 2 | Draft
FR-012 | P1-12 | Change playback speed | E3 Video | Video · Transcript | Video Player | — | — | P0 | Phase 1 | 2 | Draft
FR-013 | P1-13 | Toggle captions + language | E3 Video | Video · Transcript | Video Chrome Footer | — | EC-04 | P0 | Phase 1 | 3 | Draft
FR-014 | P1-14 | Fullscreen video | E3 Video | Video · Transcript | Video Player | — | — | P0 | Phase 1 | 2 | Draft
FR-015 | P1-15 | Download transcript | E3 Video | Video · Transcript | Video Chrome Footer | — | — | P1 | Phase 1 | 1 | Draft
FR-016 | P1-16 | See video license info | E3 Video | Video · Transcript | Video Chrome Footer | — | — | P2 | Phase 1 | 1 | Draft
FR-017 | P1-17 | Video error states | E3 Video | Edge cases wrapper | Video Player (Error variant) | — | EC-01, EC-02, EC-03 | P0 | Phase 1 | 2 | Draft
FR-018 | P1-18 | Transcript auto-scroll to active line | E4 Transcript | Video · Transcript | Transcript Line | BR-11 | — | P0 | Phase 1 | 2 | Draft
FR-019 | P1-19 | Click transcript line to seek | E4 Transcript | Video · Transcript | Transcript Line | — | — | P0 | Phase 1 | 1 | Draft
FR-020 | P1-20 | Pause auto-scroll on user scroll | E4 Transcript | Video · Transcript | Resume Follow Pill | — | — | P1 | Phase 1 | 2 | Draft
FR-021 | P1-21 | Transcript empty state | E4 Transcript | Edge cases | Empty State | — | EC-03 | P1 | Phase 1 | 1 | Draft
FR-022 | P1-22 | Add note to transcript line | E5 Notes | Video · Notes + Note Modal | Note Editor Modal | BR-11 | — | P0 | Phase 1 | 3 | Draft
FR-023 | P1-23 | Edit existing note | E5 Notes | Video · Notes + Note Modal | Note Editor Modal | — | — | P0 | Phase 1 | 2 | Draft
FR-024 | P1-24 | Delete note | E5 Notes | Video · Notes | Note Item | BR-37 | — | P0 | Phase 1 | 1 | Draft
FR-025 | P1-25 | Tag note | E5 Notes | Video · Notes + Note Modal | Tag chip + input | BR-13 | EC-08 | P0 | Phase 1 | 3 | Draft
FR-026 | P1-26 | List notes on Notes tab | E5 Notes | Video · Notes | Note Item · Empty State | — | — | P0 | Phase 1 | 2 | Draft
FR-027 | P1-27 | Note save failures + drafts | E5 Notes | Video · Notes + Note Modal | Inline Alert | — | EC-05 | P0 | Phase 1 | 2 | Draft
FR-028 | P1-28 | Orphaned note warning | E5 Notes | Video · Notes | Note Item · Warning state | BR-11 | EC-06 | P1 | Phase 1 | 1 | Draft
FR-029 | P1-29 | See downloadable files | E6 Downloads | Video · Downloads | File Item · Empty State | — | — | P0 | Phase 1 | 2 | Draft
FR-030 | P1-30 | Download a file | E6 Downloads | Video · Downloads | File Item | — | — | P0 | Phase 1 | 1 | Draft
FR-031 | P1-31 | Download failure handling | E6 Downloads | Video · Downloads | File Item · Error | — | EC-10 | P1 | Phase 1 | 1 | Draft
FR-032 | P1-32 | Bookmark from sidebar | E7 Bookmarks | All player screens | Topic Row · Bookmark Toast | BR-09, BR-10, BR-21 | — | P0 | Phase 1 | 3 | Draft
FR-033 | P1-33 | Bookmark from topbar | E7 Bookmarks | All player screens | Topbar Saved icon | — | — | P2 | Phase 1 | 1 | Draft
FR-034 | P1-34 | Bookmark persistence | E7 Bookmarks | All player screens | Backend sync | BR-09, BR-35 | — | P0 | Phase 1 | 2 | Draft
FR-035 | P1-35 | Bookmark save failure | E7 Bookmarks | All player screens | Toast (error) | — | EC-09 | P1 | Phase 1 | 1 | Draft
FR-036 | P1-36 | Open notifications panel | E8 Notifications | Notifications panel | Overlay Panel chrome | — | — | P0 | Phase 1 | 2 | Draft
FR-037 | P1-37 | Group by type + date | E8 Notifications | Notifications panel | Tab button base + Section labels | BR-14, BR-15 | — | P0 | Phase 1 | 3 | Draft
FR-038 | P1-38 | Mark notifications read | E8 Notifications | Notifications panel | Notification Item · Mark all read action | BR-16 | — | P0 | Phase 1 | 3 | Draft
FR-039 | P1-39 | Type-specific notification rendering | E8 Notifications | Notifications panel | Notification Item · Icon variants | BR-14 | — | P0 | Phase 1 | 7 | Draft
FR-040 | P1-40 | Empty notifications per tab | E8 Notifications | Notifications panel | Empty State | — | EC-18 | P1 | Phase 1 | 1 | Draft
FR-041 | P1-41 | Notification fetch error | E8 Notifications | Notifications panel | Inline Alert | — | EC-19 | P1 | Phase 1 | 1 | Draft
FR-042 | P1-42 | Open saved panel | E9 Saved | Saved panel | Overlay Panel chrome | — | — | P0 | Phase 1 | 2 | Draft
FR-043 | P1-43 | Filter saved items | E9 Saved | Saved panel | Tab button base (Button gray) | — | — | P0 | Phase 1 | 2 | Draft
FR-044 | P1-44 | Navigate from saved item | E9 Saved | Saved panel | Saved Topic + Saved Note items | — | — | P0 | Phase 1 | 2 | Draft
FR-045 | P1-45 | Saved empty + broken states | E9 Saved | Saved panel | Empty State + Warning row | — | EC-21, EC-22 | P1 | Phase 1 | 2 | Draft
FR-046 | P1-46 | Auto-complete Video at 90% | E10 Completion | Video · Transcript | Sidebar Topic Row state machine | BR-01 | — | P0 | Phase 1 | 2 | Draft
FR-047 | P1-47 | Manual complete for Reading-like | E10 Completion | Reading/Lab/Activity (P1.5) | Mark Complete button | BR-01 | — | P1 | Phase 1.5 | 1 | Draft
FR-048 | P1-48 | Module progress updates on complete | E10 Completion | All player screens | Sidebar Module Header | BR-02, BR-04, BR-06 | — | P0 | Phase 1 | 2 | Draft
FR-049 | P1-49 | Optional topics don't gate | E10 Completion | Sidebar | Topic Row · Optional badge | BR-08 | — | P0 | Phase 1 | 1 | Draft
FR-050 | P1-50 | Locked module entry blocked | E10 Completion | Player content area | Lock state | — | EC-15 | P0 | Phase 1 | 1 | Draft
FR-051 | P1-51 | Course complete modal | E11 Certificate | Course Complete Modal | Modal · Course Complete | BR-03 | — | P0 | Phase 1 | 1 | Draft
FR-052 | P1-52 | View certificate | E11 Certificate | Certificate | Certificate page | BR-25 | EC-31 | P0 | Phase 1 | 2 | Draft
FR-053 | P1-53 | Share certificate | E11 Certificate | Certificate | Share menu | BR-27 | — | P0 | Phase 1 | 2 | Draft
FR-054 | P1-54 | Print certificate | E11 Certificate | Certificate | Print button + print stylesheet | — | — | P1 | Phase 1 | 1 | Draft
FR-055 | P1-55 | Certificate verification (public) | E11 Certificate | Verify URL page | Verification page | BR-26 | EC-32 | P0 | Phase 1 | 2 | Draft
FR-056 | P1-56 | See assignment requirements | E12 Peer-graded | Peer-graded Assignment | Assignment Intro molecule | — | — | P0 | Phase 1 | 1 | Draft
FR-057 | P1-57 | Upload submission files | E12 Peer-graded | Peer-graded Assignment | File Upload Zone | — | EC-29 | P0 | Phase 1 | 5 | Draft
FR-058 | P1-58 | Submit assignment | E12 Peer-graded | Peer-graded Assignment | Submit button + confirm modal | — | — | P0 | Phase 1 | 2 | Draft
FR-059 | P1-59 | Review peer submissions | E12 Peer-graded | Peer review (P1.5) | Peer review queue | — | EC-27, EC-28 | P1 | Phase 1 | 3 | Draft
FR-060 | P1-60 | Deadline handling | E12 Peer-graded | Peer-graded Assignment | Deadline confirm modal | — | EC-30 | P1 | Phase 1 | 2 | Draft
FR-061 | P1-61 | Receive peer grade notification | E12 Peer-graded | Notifications panel | Notification Item · peer_review | BR-14 | — | P1 | Phase 1 | 1 | Draft
FR-062 | P1-62 | Pre-live state 15 min before | E13 VILT | VILT Join Live | Live Control Bar (pre-live) | BR-07, BR-22 | — | P0 | Phase 1 | 1 | Draft
FR-063 | P1-63 | Join live session | E13 VILT | VILT Join Live | Live Control Bar (live) | BR-23 | — | P0 | Phase 1 | 1 | Draft
FR-064 | P1-64 | Late join handling | E13 VILT | VILT Live | Late join indicator | — | EC-24 | P2 | Phase 1 | 1 | Draft
FR-065 | P1-65 | Post-live recording | E13 VILT | Recording (post-live) | Topic Row · Recording type | BR-24 | EC-26 | P1 | Phase 1 | 2 | Draft
FR-066 | P1-66 | Keyboard navigation | E14 A11y | All player screens | — | BR-38 | — | P0 | Phase 1 | 2 | Draft
FR-067 | P1-67 | Screen reader announcements | E14 A11y | All player screens | aria-live regions | BR-38 | — | P0 | Phase 1 | 3 | Draft
FR-068 | P1-68 | ARIA labels on icon buttons | E14 A11y | All player screens | All icon buttons | BR-38 | — | P0 | Phase 1 | 1 | Draft
FR-069 | P1-69 | WCAG AA color contrast | E14 A11y | All screens | Design tokens (LMS/*) | BR-38 | — | P0 | Phase 1 | 1 | Draft
FR-070 | P1-70 | Reduced motion respected | E14 A11y | All screens | Animation rules | BR-39 | — | P0 | Phase 1 | 1 | Draft
FR-071 | P1-71 | Touch targets ≥ 44px on mobile | E14 A11y | Mobile variants | Interactive elements | BR-38 | — | P0 | Phase 1 | 1 | Draft
FR-072 | P1-72 | Analytics events fire | E14 A11y | All screens | Analytics layer | BR-41, BR-42 | — | P0 | Phase 1 | 2 | Draft
FR-073 | P1-73 | Generic error handling | E14 A11y | App-wide | Toast + error tracking | — | EC-40 | P0 | Phase 1 | 1 | Draft
TOTAL | 73 stories | [8 empty] | 136

## Phase Summary
Phase 1 Build Summary
Epic | Stories | P0 count | AC count
E1 · Dashboard + course entry | 4 | 24 | 54
E2 · Course Player chrome | 5 | 4 | 11
E3 · Video playback | 8 | 6 | 15
E4 · Transcript + auto-scroll | 4 | 2 | 6
E5 · Notes (transcript-anchored) | 7 | 6 | 14
E6 · Downloads | 3 | 2 | 4
E7 · Bookmarks | 4 | 2 | 7
E8 · Notifications panel | 6 | 4 | 17
E9 · Saved panel | 4 | 3 | 8
E10 · Topic completion | 5 | 4 | 7
E11 · Course completion + Cert | 5 | 4 | 8
E12 · Peer-graded Assignment | 6 | 3 | 14
E13 · VILT Join Live | 4 | 2 | 5
E14 · A11y + analytics + edges | 8 | 8 | 12
TOTAL | 73 | 74 | 182

## Priority breakdown
Priority breakdown
Priority | Count | Meaning
P0 | 53 | Must-have for Phase 1 launch. No flexibility.
P1 | 17 | Should-have. Cut last if scope pressure.
P2 | 3 | Nice-to-have. Likely Phase 1.5.

## Legend
Legend + codes
Code prefix | Meaning | Source doc
FR-XXX | Functional Requirement ID — unique across the project | This RTM
P1-XX | Phase 1 User Story ID | 02-user-stories-phase1.md
E1..E14 | Epic IDs — group of related stories | 02-user-stories-phase1.md
BR-XX | Business Rule ID | 03-business-rules.md
EC-XX | Edge Case / Failure mode ID | 04-edge-cases-failures.md
P0/P1/P2 | Priority: must / should / could | PM call, can shift
Phase 1 | In current build target | 05-feature-roadmap.md
Phase 1.5 | Fast-follow within 4 weeks of Phase 1 | 05-feature-roadmap.md
Phase 2 | Engagement + scale features | 05-feature-roadmap.md
Phase 3 | Platform expansion | 05-feature-roadmap.md
Status workflow
Status | Meaning
Draft | Story drafted by design + Nelson. Not yet BA-validated.
Refined | BA reviewed + sharpened AC. Ready for estimation.
Estimated | T-shirt sized by engineering.
In Progress | Build started.
In QA | Build done, QA testing.
Done | AC verified, in production behind feature flag or live.
Blocked | Something stopping progress. See Notes.
Cut | Removed from scope. Logged for Phase 1.5+